Activity 08

Risk identification and analysis

2025-2026

Note: Be sure to include all group member's names in your submission.

## Scenario: Estimating a TravelTech Marketplace SaaS Platform

Your team has been contracted to build a TravelTech Marketplace SaaS platform that connects travel agencies, tour operators, and individual travelers. The system will allow users to:

- Discover and book curated travel experiences

- Compare prices and itineraries across providers

- Manage bookings, payments, and reviews

- Access personalized recommendations based on preferences and location

- Integrate with third-party APIs (e.g., Google Maps, Stripe, Amadeus)

The platform must be scalable, multi-tenant, and support both web and mobile interfaces.

Project Characteristics

| Attribute | Details |
| --- | --- |
| Estimated Size | 95 KLOC |
| Project Type | Embedded (high complexity, tight constraints, diverse team) |
| Development Team | 12 developers, 3 QA engineers, 1 DevOps, 1 PM |
| Timeline Expectation | 14–18 months |
| Constraints | Must support multi-currency, multi-language (Arabic, English, French), and comply with GDPR and AML laws |
| Technology Stack | Node.js (backend), React Native (mobile), PostgreSQL, Docker, Kubernetes |
| Deployment Model | SaaS with subscription tiers for agencies and operators + commissions on sales |

COCOMO Constants:

## Student Tasks

- Effort Estimation

  - Use the Basic COCOMO formula to estimate effort in person-months

- Development Time

  - Estimate the development time in months

- Team Size

  - Calculate the average team size

- Analysis & Discussion

  - Compare your results with the client’s expectations.

  - Discuss how changing the project type (Semi-detached to embedded or the opposite) would affect the estimates.

  - Reflect on the limitations of Basic COCOMO and how Intermediate COCOMO could improve accuracy.

## Intermediate COCOMO:

- Introduce cost drivers from Intermediate COCOMO:

|  | Ratings |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Very Low | Low | Nominal | High | Very High | Extra High |
| Product attributes |  |  |  |  |  |  |
| Required software reliability | 0.75 | 0.88 | 1.00 | 1.15 | 1.40 |  |
| Size of application database |  | 0.94 | 1.00 | 1.08 | 1.16 |  |
| Complexity of the product | 0.70 | 0.85 | 1.00 | 1.15 | 1.30 | 1.65 |
| Hardware attributes |  |  |  |  |  |  |
| Run-time performance constraints |  |  | 1.00 | 1.11 | 1.30 | 1.66 |
| Memory constraints |  |  | 1.00 | 1.06 | 1.21 | 1.56 |
| Volatility of the production environment (servers) |  | 0.87 | 1.00 | 1.15 | 1.30 |  |
| Required turnabout time |  | 0.87 | 1.00 | 1.07 | 1.15 |  |
| Personnel attributes |  |  |  |  |  |  |
| Analyst capability | 1.46 | 1.19 | 1.00 | 0.86 | 0.71 |  |
| Applications experience | 1.29 | 1.13 | 1.00 | 0.91 | 0.82 |  |
| Software engineer capability | 1.42 | 1.17 | 1.00 | 0.86 | 0.70 |  |
| Production environment experience ( servers technology) | 1.21 | 1.10 | 1.00 | 0.90 |  |  |
| Programming language experience | 1.14 | 1.07 | 1.00 | 0.95 |  |  |
| Project attributes |  |  |  |  |  |  |
| Application of software engineering methods | 1.24 | 1.10 | 1.00 | 0.91 | 0.82 |  |
| Use of software tools | 1.24 | 1.10 | 1.00 | 0.91 | 0.83 |  |
| Required development schedule | 1.23 | 1.08 | 1.00 | 1.04 | 1.10 |  |

- Adjust your estimates based on selected drivers and justify your choices.

# Submission

Be sure to include all group members' names in your submission.